# Q3 — Program Charter

MIRA — AI-Powered Project Intelligence Assistant

# 1. Vision

Give Nexora PMs/TPMs an always-available assistant that converts raw project data into structured, grounded and actionable project intelligence.

# 2. Scope

## In Scope

Five-agent capability set

Router orchestration

Grounded project-data ingestion

Weekly status automation

Milestone/blocker alerts

Langfuse observability

Baseline evaluation

## Out of Scope

Live Jira/Trello write-back

Fine-tuning in the initial release

Autonomous external stakeholder communications without human review

# 3. Success Criteria

| Objective | Target |
| --- | --- |
| Planning effort | ≤15 minutes |
| Weekly status effort | ≤5 minutes |
| Current risk matrix coverage | 100% |
| Grounding accuracy | 100% |
| Routing accuracy | ≥95% |
| Pre-retrospective at-risk/blocked detection | ≥90% |
| Adoption | ≥8 of 10 PMs/TPMs within one quarter |

# 4. Indicative Timeline

| Phase | Duration | Milestone |
| --- | --- | --- |
| Discovery & design | Weeks 1–2 | Architecture/orchestration approved |
| Core build | Weeks 3–5 | Planner, Risk and Status end-to-end |
| Extended + observability | Weeks 6–7 | Milestone, Stakeholder Update, Langfuse |
| Evaluation & hardening | Week 8 | Baseline and evaluation completed |
| Pilot | Weeks 9–10 | 3 PM pilot |
| Full rollout | Weeks 11–12 | PM/TPM onboarding |

# 5. Risks

| Risk | Mitigation |
| --- | --- |
| Invented facts / hallucination | Grounding prompts, deterministic counts, human review |
| LLM cost overruns | Router pattern, small model, token monitoring |
| Duplicate/stale source files | Single-source folder, trashed=false, file discipline |
| API credit/rate-limit outage | Alerts, budget management, fallback key |
| Low adoption | Pilot, champions, training |
| Project-data privacy | Data-handling policy, least privilege, provider-term review |

# 6. Stakeholders & Decision Making

| Stakeholder | Interest / Role |
| --- | --- |
| CTO | Sponsor, steering and sign-off |
| PMs / TPMs | Users, pilot and feedback |
| Data/ML teams | Technical input and validation |
| Product stakeholders / clients | Recipients of outputs |
| Security / Compliance | Privacy and data-handling review |

RACI stated in the supplied documentation: AI PM/TPM = Responsible; CTO = Accountable; Security and senior PMs = Consulted; PMs = Informed.

# 7. Rollout

Pilot with 3 PMs

Collect feedback and trace data

Tune prompts/routing

Confirm baseline tests

Onboard broader PM/TPM group

Sustain with weekly quality/cost review